## All Data
1 | Service Allignment | ReleaseId | Release Name | RFC Id | Status | RFC Title | Submitted by | Submitted Date | RFC Start Date | RFO End Date
2 | Cisco Commerce | R20035 | Q2FY20 Cisco Commerce PR1 | CHG0148165 |  | FY20 November 24 Release Event - Cisco Commerce - DMPROD-Application DT | mkrothap | 11/17/2019 05:09:44 PM | 11/24/2019 12:00:00 AM | 11/24/2019 06:00:00 PM
3 | Customer Care | R20008 | CC_SCM_ Nov_FY20PR_Rel | CHG0151459 | Closed | FY20 November 24 Release Event - Customer Care - CSFPRD Non-Downtime Transition Activities | chrimar2 | 11/15/2019 10:15:31 PM | 11/24/2019 08:00:00 AM | 11/24/2019 11:00:00 AM
4 | Customer Care | R20088 | Entitlement Base | CHG0151459 | Closed | FY20 November 24 Release Event - Customer Care - CSFPRD Non-Downtime Transition Activities | chrimar2 | 11/15/2019 10:15:31 PM | 11/24/2019 08:00:00 AM | 11/24/2019 11:00:00 AM
5 | Customer Care | R20063 | GSLO FY20 November PR | CHG0151584 | Closed | FY20 November 24 Release Event - Customer Care - PSDPRD Application Downtime Activities | chrimar2 | 11/20/2019 08:49:20 AM | 11/24/2019 08:00:00 AM | 11/24/2019 11:00:00 AM
6 | Data & Information Management | R20016 | EDW_DRRNG_Enhancements_NOVFY20 | CHG0154070 | Closed | FY20 November 27 Release Event { EDWTDPROD; EDWTDPROD2} - Non DT - Data & Information Management | prsarang | 11/20/2019 08:27:58 PM | 11/27/2019 11:00:00 AM | 11/27/2019 06:00:00 PM
7 | Data & Information Management | R20027 | EDW_Nov_ACQ_Nano_Release | CHG0154070 | Closed | FY20 November 27 Release Event { EDWTDPROD; EDWTDPROD2} - Non DT - Data & Information Management | prsarang | 11/20/2019 08:27:58 PM | 11/27/2019 11:00:00 AM | 11/27/2019 06:00:00 PM
8 | Data & Information Management | R20030 | EDW_Recurring Revenue_Metrics_Enhancement | CHG0154070 | Closed | FY20 November 27 Release Event { EDWTDPROD; EDWTDPROD2} - Non DT - Data & Information Management | prsarang | 11/20/2019 08:27:58 PM | 11/27/2019 11:00:00 AM | 11/27/2019 06:00:00 PM
9 | Data & Information Management | R20081 | EDW_Services_Hana_27Nov19_Release | CHG0154070 | Closed | FY20 November 27 Release Event { EDWTDPROD; EDWTDPROD2} - Non DT - Data & Information Management | prsarang | 11/20/2019 08:27:58 PM | 11/27/2019 11:00:00 AM | 11/27/2019 06:00:00 PM
10 | Data & Information Management | R20059 | EDW Global Partner Version 1 | CHG0154070 | Closed | FY20 November 27 Release Event { EDWTDPROD; EDWTDPROD2} - Non DT - Data & Information Management | prsarang | 11/20/2019 08:27:58 PM | 11/27/2019 11:00:00 AM | 11/27/2019 06:00:00 PM
11 | Supply Chain Management | R20020 | SC Q2FY20 Nov Plan BI CDO Refresh and Order Variability changes | CHG0154070 | Closed | FY20 November 27 Release Event { EDWTDPROD; EDWTDPROD2} - Non DT - Data & Information Management | prsarang | 11/20/2019 08:27:58 PM | 11/27/2019 11:00:00 AM | 11/27/2019 06:00:00 PM
12 | xRM | R20106 | PSS banner Partner Admins | CHG0157846 | Assess | FY20 November 29 Release Event - xRM / CPP & SCCC - PDBPROD - App DT | ukarmaka | 11/25/2019 10:22:57 AM | 11/29/2019 03:00:00 AM | 11/29/2019 09:00:00 AM
13 | Customer Care | R20117 | MCE AM | CHG0159656 | Closed | FY20 November 30 Release Event - Customer Care - CSFPRD - Non-Downtime activities | baravi | 11/27/2019 01:58:18 PM | 11/30/2019 08:30:00 AM | 11/30/2019 11:30:00 AM
14 | Cisco Partner Prog (CPP) & Sales Coverage Credit & Compensation (SCCC) | R20029 | NCE Q2FY20 Nov | CHG0155386 | Closed | FY20 December 01 Release Event - xRM / CPP & SCCC - G2CPRD - App DT (OTM SCE) | ukarmaka | 11/22/2019 11:50:25 PM | 12/01/2019 07:00:00 AM | 12/01/2019 12:30:00 AM
15 | Order to Cash & Financial Services | R20055 | Concur Russia Travel Release | CHG0162750 | Closed | FY20 December 03 Release Event - Order To Cash & Financial Services - Procure To Pay, Accounting and Finance-FNTR3PRD Non DownTime | aggerwal | 12/02/2019 07:11:38 PM | 12/03/2019 07:30:00 PM | 12/03/2019 09:30:00 PM
16 | Cisco Commerce | R20128 | Commerce_DecFY20_NanoRelease_12_04 | CHG0160908 |  | FY20 December 4 Release Event - Cisco Commerce - PICA ( DMPROD) - Application DT | mmogavee | 11/29/2019 02:23:36 PM | 12/05/2019 04:30:00 AM | 12/05/2019 07:30:00 AM
17 | Customer Care | R20064 | GSLO FY20 December Release | CHG0158699 | Closed | FY20 December 08 Release Event - Customer Care - PSDPRD Downtime Transition activities | romadath | 11/27/2019 10:55:50 AM | 12/08/2019 06:00:00 AM | 12/08/2019 12:00:00 AM
18 | Customer Care | R20064 | GSLO FY20 December Release | CHG0157739 | Closed | FY20 December 08 Release Event - Customer Care - CSFPRD - Down time Transition Activities | romadath | 11/27/2019 10:49:56 AM | 12/08/2019 05:30:00 AM | 12/08/2019 12:00:00 AM
19 | Customer Care | R20054 | Foundational_Services_Dec_20 | CHG0157739 | Closed | FY20 December 08 Release Event - Customer Care - CSFPRD - Down time Transition Activities | romadath | 11/27/2019 10:49:56 AM | 12/08/2019 05:30:00 AM | 12/08/2019 12:00:00 AM
20 | Customer Care | R20156 | FY20 December 08 ERMO Release | CHG0158699 | Closed | FY20 December 08 Release Event - Customer Care - PSDPRD Downtime Transition activities | romadath | 11/27/2019 10:55:50 AM | 12/08/2019 06:00:00 AM | 12/08/2019 12:00:00 AM
21 | Customer Care | R20118 | Entitlement Framework | CHG0159505 | Closed | FY20 December 08 Release Event - Customer Care - CSSWPRD - EF BSE UI Internal application down time Activities | romadath | 11/27/2019 10:58:59 AM | 12/08/2019 08:00:00 AM | 12/08/2019 10:00:00 AM
22 | Customer Care | R20111 | Entitlement Base FY20 Dec 08 | CHG0157739 | Closed | FY20 December 08 Release Event - Customer Care - CSFPRD - Down time Transition Activities | romadath | 11/27/2019 10:49:56 AM | 12/08/2019 05:30:00 AM | 12/08/2019 12:00:00 AM
23 | Customer Care | R20121 | CSFPRD Node 7 and 9_Bug fix | CHG0157739 | Closed | FY20 December 08 Release Event - Customer Care - CSFPRD - Down time Transition Activities | romadath | 11/27/2019 10:49:56 AM | 12/08/2019 05:30:00 AM | 12/08/2019 12:00:00 AM
24 | Customer Care | R20003 | CSD_PEP_FY20_DEC_REL | CHG0158911 | Closed | FY20 December 08 Release Event - Customer Care - SPMPRD - PEP application Non DT activities | raghasri | 11/27/2019 07:49:01 AM | 12/08/2019 07:00:00 AM | 12/08/2019 02:00:00 PM
25 | Customer Care | R20083 | CSD FF PSA DEC FY20 | CHG0157739 | Closed | FY20 December 08 Release Event - Customer Care - CSFPRD - Down time Transition Activities | romadath | 11/27/2019 10:49:56 AM | 12/08/2019 05:30:00 AM | 12/08/2019 12:00:00 AM
26 | Customer Care | R20061 | CSD AS BME DEC FY20 | CHG0157739 | Closed | FY20 December 08 Release Event - Customer Care - CSFPRD - Down time Transition Activities | romadath | 11/27/2019 10:49:56 AM | 12/08/2019 05:30:00 AM | 12/08/2019 12:00:00 AM
27 | Cisco Partner Prog (CPP) & Sales Coverage Credit & Compensation (SCCC) | R20026 | LCI Performance Dashboard | CHG0152552 | Closed | FY20 December 08 Release Event - xRM / CPP & SCCC - PDBPROD - App DT (PMF, PPA, TPV, PPE) | sudsilva | 11/21/2019 09:08:49 AM | 12/07/2019 03:00:00 AM | 12/07/2019 11:00:00 AM
28 | Data & Information Management | R20109 | EDW_JOB_REQUISITIONS | CHG0155524 |  | FY20 December 08 Release Event - Data & Information Management - {EDWTDPROD, EDWTDPROD2} - Non Downtime | prsarang | 11/26/2019 02:00:08 PM | 12/07/2019 04:00:00 AM | 12/08/2019 08:00:00 PM
29 | Data & Information Management | R20132 | Q2FY20 DEC Release | CHG0148338 | Closed | FY20 December 08 Release Event - Supply Chain Management - CG1PRD - DT | abnaraya | 11/17/2019 09:56:02 AM | 12/08/2019 06:00:00 AM | 12/08/2019 05:00:00 PM
30 | Cisco Partner Prog (CPP) & Sales Coverage Credit & Compensation (SCCC) | R20034 | SC3 OTB Nov03 | CHG0156586 | Assess | FY20 December 08 Release Event - xRM / CPP & SCCC - G2CPRD - App DT (OTM SCE / OneCAT) | sairayap | 11/26/2019 10:33:36 PM | 12/08/2019 07:00:00 AM | 12/08/2019 01:30:00 PM
31 | Cisco Partner Prog (CPP) & Sales Coverage Credit & Compensation (SCCC) | R20122 | CLI Q2FY20 Dec | CHG0156586 | Closed | FY20 December 08 Release Event - xRM / CPP & SCCC - G2CPRD - App DT ( OneCAT) | sairayap | 11/26/2019 10:33:36 PM | 12/08/2019 07:00:00 AM | 12/08/2019 01:30:00 PM
32 | Customer Care | R20057 | CC_SCM_Dec_FY20_Rel | CHG0157739 | Closed | FY20 December 08 Release Event - Customer Care - CSFPRD - Down time Transition Activities | romadath | 11/27/2019 10:49:56 AM | 12/08/2019 05:30:00 AM | 12/08/2019 12:00:00 AM
33 | Customer Care | R20085 | CSD_DCP2.0_DEC_REL | CHG0158611 | Closed | FY20 December 08 Release Event - Customer Care - CSFPRD & SPMPRD - DCP App DT activities (DB Non DT) | raghasri | 11/27/2019 08:16:58 AM | 12/08/2019 08:30:00 AM | 12/08/2019 08:30:00 PM
34 | Customer Care | R20085 | CSD_DCP2.0_DEC_REL | CHG0157739 | Closed | FY20 December 08 Release Event - Customer Care - CSFPRD - Down time Transition Activities | romadath | 11/27/2019 10:49:56 AM | 12/08/2019 05:30:00 AM | 12/08/2019 12:00:00 AM
35 | Customer Care | R20090 | TKL | CHG0158629 |  | FY20 December 08 Release Event - Customer Care - SPMPRD - TKL application Non DT Activities | raghasri | 11/27/2019 10:18:49 AM | 12/08/2019 09:00:00 AM | 12/08/2019 02:30:00 PM
36 | Customer Care | R20096 | GSLO FY20 December 6 SREWB Release | CHG0160239 |  | FY20 December 08 Release Event - Customer Care - PSDPRD - SRE WB App Non-Downtime Transition Activities | abimohap | 11/28/2019 01:03:38 PM | 12/06/2019 05:00:00 PM | 12/07/2019 05:00:00 AM